# Daily Construction Report

# 1. Climate

| Date | Weather | Wind force | Water level | Min/Max temp. |
| --- | --- | --- | --- | --- |
| Apr. 7, 2026 | Cloudy | Breeze | 310.72 | 23℃/37℃ |

# 2. On-site Construction Activities

Daily Construction Statistics Table

| S/N | Construction Area | Activities |  | Quantities Completed | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Right Bank Roads | Subgrade excavation, leveling and compaction for R2 Road Section K1+440-K1+740 |  | 800m³ |  |
|  |  | Concrete Curing, backfilling, and acceptance of the foundation pit behind the retaining wall in Section K2+040-2+095 |  | 1 item |  |
|  |  | Concrete Pouring for the first layer foundation of K2+765 box culvert |  | 81m³ |  |
|  |  | Formwork fabrication, shoring, and bearing capacity testing for the retaining wall foundation in Section K2+850-2+870 |  | 1 item |  |
|  |  | Road grading and maintenance, and Dust Suppression via Watering for R2 Road |  | 1 item |  |
| 2 | Right Bank Aggregate System | Rebar Tying for primary and secondary crushing workshops and D-type counterweight retaining wall |  | 1 item |  |
|  |  | Structural excavation for 2# and 3# Screening Workshops |  | 1 item |  |
|  |  | Normal concrete pouring for cushion layer and related areas of the Sand Making workshop |  | 15m³ |  |
| 3 | Right Bank Batching System | Post-pouring Curing and formwork dismantling for foundation raft slabs and foundation columns of 2# and 3# batching plants |  | 1 item |  |
|  |  | Formwork erection and Curing for silo foundations at EL.368.57m and EL.375m |  | 1 item |  |
|  |  | Rebar Tying and formwork erection for precast cover slabs at EL.375m |  | 1 item |  |
|  |  | Installation of rock bolt drainage pipes, Grouting, and steel plate welding at EL.375m-387m |  | 1 item |  |
| 4 | Right Bank Abutment | Formwork installation, Concrete Pouring, and Curing for grid beams at EL.409.15m-394.15m |  | 1 item |  |
|  |  | Concrete curing for side walls of intercepting ditch and road maintenance |  | 1 item |  |
|  |  | Earth Excavation for slope below EL.394.15m |  | 540m³ | 27 Truckloads |
| 5 | Right Bank Foundation Pit | D/S Approach Channel | Earth Excavation above EL.342m | 180m³ | 45 Truckloads |
|  |  | Longitudinal Cofferdam. | Rock Excavation at EL.317-298m | 9600m³ | 480 Truckloads |
|  |  | Hole drilling for the Longitudinal Cofferdam |  | 100 holes |  |
|  |  | Rebar and formwork installation, cleaning, and Concrete Pouring for the approach channel grid beams |  | 13.5m³ |  |

## Excavation Volume of Right Bank Foundation Pit

| Date | Units | Quantities Completed | Remarks |
| --- | --- | --- | --- |
| 4.7 | m³ | 11040 |  |
| Total |  | 803138m³ |  |

# 3. On-site Manpower and Equipment

## 3.1. Manpower

| S/N | Staff type | Actual deployment |  |  | Remarks |
| --- | --- | --- | --- | --- | --- |
|  |  | Foreign | Local | Subtotal |  |
| I | Project management | 77 | 79 | 156 |  |
| 1) | Manager | 9 | 0 | 9 |  |
| 2) | Functional departments | 68 | 79 | 147 |  |
| II | Field Construction Personnel | 231 | 563 | 794 |  |
| Total |  | 308 | 642 | 950 |  |

## 3.2. Equipment

| Equipment | Unit | Qty. | Running hrs. | Remarks |
| --- | --- | --- | --- | --- |
| Backhoe Excavator (1.0~2.0m³) | Set | 38 | ## 16h | 1 unit was deployed at the Right Bank Abutment, and 4 units were deployed at the Right Bank Foundation Pit Area. |
| Loader (3.0m³) | Set | 7 | ## 8h |  |
| 25t Dump Truck | Set | 77 | ## 16h | 2 unit was deployed at the Right Bank Abutment, and 21 units were deployed at the Right Bank Foundation Pit Area. |
| Bulldozer | Set | 6 | ## 8h |  |
| Road Roller | Set | 5 | ## 8h |  |
| Grader | Set | 6 | ## 8h |  |
| Water Truck | Set | 6 | ## 8h |  |
| Others | Set | 51 | / |  |
| Total | Set | 196 | / |  |

# 4. Records of Important Matters

| S/N | Content | Remarks |
| --- | --- | --- |
| 1 | / |  |

# 5. Environmental Health and Safety (EHS) Work

| S/N | Content | Remarks |
| --- | --- | --- |
| 1 | No safety hazards were identified during today's site operations | / |

# 6. Site Construction Pictures

| {img} | {img} |
| --- | --- |
| Backfilling of Foundations for Screening Workshop No. 2 and 3 of the Aggregate System | Slope Trimming of the Right Bank Abutment |
| {img} | {img} |
| Earth Excavation of the Right Bank Foundation Pit | Earth Excavation of the Right Bank Approach Channel |

# 7. Next day's Work Plan

| S/N | Construction Area | Activities | Planned Qty. | Remarks |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |

# 8. Pending Issues

| S/N | Content | Remarks |
| --- | --- | --- |
| 1 | / | / |

# 9. Barometer

| Period | Rainfall | Remarks |
| --- | --- | --- |
| / | / | / |

Recorded by: Liu Haosheng

Date: 2026/4/7